## Slide 1: Transparency Advisory Council Meeting
February 22, 2023

## Slide 2: Agenda
Welcome
Progress So Far
Further Plans for 2023
Highlight of Challenges

## Slide 3
Progress Report

## Slide 4: What We’ve Done Since our Last Meeting
Dashboard data has been refreshed with all year 2022 data
People Served Dashboard
Cost Data
Published select cost benchmarks for 2020 and 2021*
In process of publishing Medicaid Category of Expenditure for state fiscal year 2013-2022 on the Open Data Portal
Quality Data
Published HEDIS medical, dental, and behavioral health quality measures from 2018-2020*
* Data can be found here

## Slide 5: People Served – Beta Version

## Slide 6: Cost Transparency
Publishing 10-year Medicaid COS expenditure data on the Open Data Portal.
Create Tableau visualizations with the same dataset
Current Data
Proposed Upgrades

## Slide 7
Quality Transparency
Medical
Dental
Behavioral
Published FY 2018-2020 HEDIS measures for:

## Slide 8
Further 2023 Plans

## Slide 9: What We Plan on Doing in 2023
Update HEDIS data to include 2021 data in March
Refresh report with 2022 data in July
Expand to include new measures such as
  prevalence rates of acute and chronic diseases*
  utilization for chronic diseases
  Inpatient utilization for chronic diseases
  follow-up after ED visits
Quality Data
Update cost data with 2022 data by July
Refresh COS expenditure data with SFY 2023 data by July
Financial
People Served Dashboard
*DM, HTN, Asthma, COPD, CAD, mental health disorders, obesity, cancer, substance use disorder
Additional filtering parameters
Continued updating with CY 2023 data

## Slide 10
Highlight of Challenges

## Slide 11: High-Level Challenges So Far
Data is fragmented across various internal systems ( Data warehouse, QM Eval, Exhibit E reports, MAR reports, etc.) and ASOs
Technology
People
Insufficient people with the requisite expertise to pull the data together (for instance, query the data from the warehouse) and produce the needed quality measures
People with expertise within DSS have limited bandwidth to support effort
Process
Absence of established mechanism to pull together existing data within DSS systems
Lengthy process to obtain data from various sources
Legal/procedural barriers to securing data external to DSS - for instance data held by DPH